## Read me
Bow Tie: import template
Fill in the yellow cells on the Controls sheet, then save that sheet as CSV (File, Save As, CSV UTF-8).
In Bow Tie press Import and pick the file.
One row per control
Side says which half of the diagram it sits on: Prevent for a source on the left, Mitigate for a consequence
on the right. Pathway is the source or the consequence itself. Repeat the pathway name down the rows and the
tool groups them, in the order they first appear.
Escalation factors
A control with one escalation factor goes on the same row. A control with more than one gets extra rows
underneath it: repeat the Side and Pathway, leave Control blank, and fill only the last two columns. A blank
Control means "the one above".
An escalation factor is what would stop the control working. The escalation control is what manages that.
It is easy to skip, and it is where most of the learning is.
Existing or Proposed. This one matters.
Status must be honest. Mixing proposed treatments in with existing controls produces a diagram showing a
well-defended risk that is not defended, which is the most damaging error available in this method.
The tool keeps them apart: the header switch flips between what stands today and what your treatments
would buy. That only works if this column is right.
Owner and Evidence
Owner is a person, not a department. A control owned by Operations is owned by nobody.
Evidence is where it is written down: a test record, an audit finding, an inspection log, a procedure number.
Ask of anything you list: what records that it exists, and how would its failure come to light?
If neither has an answer, it is an intention, not a control.
What the tool does not import
The event, the scope, the risk register link and the review trigger. Type those into the tool, which asks
for them in the inspector when nothing is selected.

## Controls
Side | Pathway | Control | Type | Status | Owner | Evidence | Effectiveness | Escalation factor | Escalation control
Prevent | Tailgating through the main entrance | Speed gates with anti-tailgate detection | Prevention | Existing | Head of Facilities | Commissioning record GATE-04, annual retest | Effective | Gates propped open during deliveries | Delivery procedure requires a marshal on the gate line while it is held open.
Prevent | Tailgating through the main entrance | Reception challenge procedure | Prevention | Existing | Reception Team Leader | SOP-12, spot-checked quarterly | Partly effective
Prevent | Forced entry through a service door out of hours | Door-forced alarm to the control room | Detection | Existing | Security Manager | Alarm test log, monthly | Effective | Control room unstaffed on the night shift | Minimum staffing standard written into the guarding contract.
Prevent | Forced entry through a service door out of hours | [6 empty] | Alarm cable shares the door frame with the lock | Cable route surveyed and re-routed at the next refurbishment.
Prevent | Visitor left unescorted after being badged in | Escort policy with sign-out at reception | Prevention | Proposed | Reception Team Leader |  | Not rated
Mitigate | Client equipment tampered with or removed | Camera coverage of every aisle, recorded | Detection | Existing | Security Manager | Coverage survey CS-2, retention set at 90 days | Effective
Mitigate | Service outage affecting tenants | Failover to the second hall | Recovery | Existing | Head of Infrastructure | Failover test report, six-monthly | Effective